# AI FitTrack Project Planning

Phase 4

This plan organizes the completed backend work into dependency-based gates without inventing dates, team assignments or responsibilities that were not supplied.

| Field | Value |
| --- | --- |
| Project | AI FitTrack |
| Submission | SmartBridge Naan Mudhalvan |
| Project scope | Backend-only REST API |
| Technology | Node.js, Express.js, MongoDB, Mongoose, JWT and Google Gemini AI |
| Source baseline | Latest uploaded backend ZIP and supplied verification evidence |
| Document status | Submission-ready content; student metadata and final video links remain pending |

Prepared for academic evaluation. Secrets, credentials, private environment files and unverified claims are excluded.

# Document contents

1. Planning approach

2. Work breakdown

3. Deliverables

4. Dependencies

5. Quality and risk plan

6. Roles and submission gates

# Planning approach

Because the source package does not contain an approved calendar or team allocation, this plan uses ordered completion gates. Each gate has a measurable output and acceptance condition. Dates and assignees must be added only after the student or team confirms them.

Figure 1  Dependency-based project gates without unverified dates

# Work breakdown structure

| Gate | Work package | Deliverable | Acceptance evidence |
| --- | --- | --- | --- |
| 1 | Scope and requirements | Problem statement, objectives, actor and requirement list | Official document mapped to 24 backend requirements |
| 2 | Architecture and data | Layer design, API design, User and Workout schemas | Source folders, schema constraints and diagrams agree |
| 3 | Authentication and database | MongoDB connection, User model, bcrypt, JWT, profile | Registration, login, profile and unauthorized evidence |
| 4 | Workout module | CRUD, search, validation and ownership | Eight live workout records plus automated tests |
| 5 | Gemini AI module | Recommendation, submitted insights and database insights | Three live sanitized Gemini response records |
| 6 | Verification and submission | Tests, documentation, repository and demonstration | 95 automated passes recorded; final links still pending |

# Planned deliverables

Backend source with dependency lockfile and safe .env.example.

Postman collection containing health, authentication, workout and AI requests.

Automated tests for authentication, workouts, validation, security and Gemini retry behavior.

Sanitized live verification records with no passwords, tokens, database credentials or API keys.

Eight-phase DOCX and PDF documentation set.

Public GitHub repository and student-recorded demonstration video after final upload.

# Dependency plan

| Dependency | Needed by | Control |
| --- | --- | --- |
| Node.js 20+ and npm | All development and tests | Use engines declaration and package-lock.json. |
| MongoDB | Auth and workout persistence | Connect before server listen; fail with actionable error. |
| JWT secret | Registration, login and protected routes | Fail at startup if absent; recommend at least 32 characters. |
| Gemini API key | AI recommendation and insights | Return safe 503 when absent; do not expose the key. |
| Network access | Atlas and Gemini live checks | Use local mocked tests when external services are unavailable. |
| Postman or HTTP client | Demonstration and manual verification | Run the collection in the documented order. |

# Risk register

| Risk | Likelihood | Impact | Implemented or planned response |
| --- | --- | --- | --- |
| Credential exposure | Medium | High | Commit only .env.example; hide terminal and Postman environment values during recording. |
| Atlas connection failure | Medium | High | Configurable DNS, IPv4 option, timeout and clear startup failure. |
| Gemini quota or downtime | Medium | Medium | Bounded retries, timeout, rate limit and safe normalized errors. |
| Cross-user data access | Low | High | JWT user reload and owner-scoped queries; automated isolation tests. |
| Invalid client input | Medium | Medium | Controller validation plus Mongoose validation and standard 400 responses. |
| Evidence mismatch after code change | Medium | Medium | Re-run Postman evidence after the final ZIP is frozen. |
| Missing submission identity or URLs | High | Medium | Complete the pending metadata checklist before upload. |

# Quality plan

Review requirement-to-source traceability before declaring completion.

Keep password, token and API-key values out of evidence and documentation.

Run automated tests, smoke checks, Atlas checks and live Gemini checks on the frozen release.

Verify response envelopes and status codes in Postman.

Inspect DOCX and PDF output for clipping, unreadable tables and missing figures.

Confirm the public repository excludes node_modules and every private .env file.

# Role allocation template

| Work area | Suggested responsibility | Confirmed assignee |
| --- | --- | --- |
| Requirements and documentation | Maintain traceability and final report | Not supplied |
| Backend and database | Maintain Express, Mongoose and MongoDB behavior | Not supplied |
| Authentication and security | Review JWT, bcrypt, CORS and isolation | Not supplied |
| Gemini integration | Validate prompts, schema, retries and safety | Not supplied |
| Testing and demonstration | Run evidence flow and record video | Not supplied |

# Items requiring student confirmation

| Pending item | What to provide |
| --- | --- |
| Student identity | Name, NM ID, register or roll number and department were not present in the supplied project files. |
| Institution details | College name, academic year, guide or mentor name and official submission date need confirmation. |
| Team details | Team name, member list and responsibility allocation were not supplied; no ownership is assigned in these documents. |
| Repository | Insert the final public GitHub repository URL after upload. |
| Deployment | Insert the deployed API base URL if the evaluator requires a hosted demonstration. |
| Demonstration video | Record the video using Phase 8 and insert the final shareable video URL. |